## Sheet1
Date | Proccess finished | Proccess started | Status
2023-02-20 | Completed design and main idea formulation. Documentation review completed. | Git repos inited. Started the VPN-prototyping.
2023-02-27 | Completed VPN-server prototype. Documentation added. | Started VPN-server docker adaptation.
2023-03-06 | VPN-server prototype first launch on VPS. Test connection successfully established over Wireguard client. Configuration modifing over API commands successfully tested. | Started the main server prototyping.
2023-03-13 | Main server minimal prototype ready. Code review completed. Documentation added. | Started the main server code clean-up and additional features adding.
2023-03-20 | Main server first-launched on VPS. Communications over API commands tested. Communication with VPN-server tested. | Started the website prototyping.
2023-03-27 | Website UI prototype ready, not fully functional. | Continuing website development.
2023-04-03 | Website UI prototype ready. First launch on VPS. Communication with main server tested. | Desktop application prototyping started.
2023-04-10 | Desktop application UI and webclient ready. | Continuing desktop app development. Adding wireguard service.
2023-04-17 | Desktop app ready. Fully functional minimum valuable product ready. | Starting mobile app development. Learning Kotlin docs.
2023-04-24 | Kotlin docs completed. | Actual start of mobile app prototyping (by writing the code).
2023-05-01 | Android mobile app ready & tested. | Total project review started.
2023-05-08
2023-05-15
2023-05-22
2023-05-29
2023-06-05